CONTRACTOR’S SITE PROGRESS REPORT

UPGRADING OF SONDA – DUNDUZU M1 ROAD AND CONSTRUCTION OF LUNYANGWA BRIDGE IN MZUZU CITY

PROCUREMENT REFERENCE No: MCC/WORKS/BRG/21/07/01 LOT 2

04th May, 2023

- CONTRACT DETAILS

  - Name of Contractor		:	SOS CONSTRUCTION

  - Contract Sums			:	MWK  5,856,857,885.77

  - Contract Duration		:	1095 Days

  - Commencement Date		:	04th JULY, 2022

  - Initial Completion Date		:	02nd JULY, 2025

  - Revised Completion Date	:

  - Time Elapsed			:	304 Days

  - Time Remaining		:	791 Days

- WORKS IN PROGRESS

  - Surveying

  - Stock piling of materials

- WORKS DONE

  - Cut to spoil from 0+000 – 2+700

  - Roadbed preparation from 0+000 – 2+700

  - Clearing and Grubbing from 0+000 – 5+840

  - Fill on the Gully – completed

  - Selected fill 0+000 – 2+700

  - Subbase 0+000 – 2+000

  - Construction of box culvert 0+020

  - Construction of bush check dams

- PERSONELL

In place

- MATERIALS/RESOURCES

- gravel

- PLANTS & EQUIPMENTS

In place

- QA/QC

    - test are being conducted and results submitted

- CRITICAL ISSUES AND CHALLENGES

    - Delay of payments

    - Escalation

- INFORMATION REQUIRED BY CONTRACTOR

    - Updated works order

    - Design

    - Update on IPC 2 & 4

- PROGRESS SUMMARY

  - Physical

    - 19.03%

  - Time elapsed (to date 04/05/23)

    - 27.76%

  - Financial

|  | IPC 1 | IPC 2 | IPC3 |
| --- | --- | --- | --- |
| IPC amounts | 964,091,833.05 | 149,153,538.33 | 149,442,387.62 |
| Cumulative Percentage Progress | - | 3% | 5% |
| Status | Paid | Not paid | Paid |
| Date Submitted | 27/07/2022 | 06/10/2022 | 13/12/2022 |
| Date Paid | 10/11/2022 | - | 28/04/2023 |

|  | IPC 4 |  |  |
| --- | --- | --- | --- |
| IPC amounts | 104,580,926.77 | - | - |
| Cumulative Percentage Progress | 7% | - | - |
| Status | Not paid | - | - |
| Date Submitted | 07/02/2023 | - | - |
| Date Paid | - | - | - |

- ENVIRONMENTAL, HEALTH AND SAFETY ISSUES

- We conducted sensitization meeting on 26th January 2023